## Test Data
Item | Module | Scenario | Steps | Expected
Accounts | Preparation | Prepare accounts | owner1, owner2, requester1, approver1, approver2, groupUser1, groupUser2, reporter1, viewer1, noAccessUser | Each account can login and has expected base access
Workflow | Preparation | Prepare sample workflow | WF-UAT-01 with requester input step, approval steps, and final step | Workflow can cover all UAT flows
Fields | Preparation | Prepare field types | text, textarea, number, date, datetime, boolean, select, multi-select, file, stored-procedure, table | All field render/save/report cases can be tested

## Designer
A. Workflow Designer / Configuration
ID | Scenario | Steps | Expected
WF-001 | Create workflow | Owner creates workflow with code, name, mail, profile, version mode | Workflow is created and visible in Designer
WF-002 | Required validation | Leave code/name empty when creating workflow | UI/API shows required validation and workflow is not created
WF-003 | Edit workflow | Edit name, description, active/public, mail/profile | Save succeeds and reload shows updated values
WF-004 | Public workflow | Set Public for requesters | User without permission can see workflow in Start Request
WF-005 | Non-public workflow | Disable public and do not grant User permission | User cannot see workflow in Start Request
WF-006 | Add permission User | Grant User to requester | Requester can see and create request
WF-007 | Add permission Owner | Grant Owner to owner2 | owner2 can see Designer and approve version
WF-008 | Add permission Viewer | Grant Viewer to viewer1 | viewer1 can view config/detail but cannot edit
WF-009 | Add permission Reporter | Grant Reporter to reporter1 | reporter1 can see Reports only
WF-010 | Add group | Create group with code, name, members | Group and members display correctly
WF-011 | Permission by group | Grant permission with PrincipalType Group | Group members receive the permission
WF-012 | Delete group | Delete group | Group is deleted or API returns clear constraint error
WF-013 | Add step | Create step with order, code, name, approval type/mode | Step appears correctly in workflow detail
WF-014 | Delete step | Delete step with fields | Step and fields disappear without UI error
WF-015 | Add field | Create fields for all data types | Fields render correctly in request form
WF-016 | Delete field | Delete configured field | Field no longer appears in new forms/detail/report
WF-017 | Conditional field | Configure visibleWhen/requiredWhen | Field only shows and becomes required when condition matches
WF-018 | Table field schema | Select table field type | Validation JSON template is suggested and schema saves

## Version
B. Version / History
ID | Scenario | Steps | Expected
VER-001 | Draft version auto-created | Edit workflow/step/field/group/rule | Draft version is created or updated with change summary
VER-002 | Submit version | Owner submits draft version | Version becomes PendingApproval
VER-003 | Same owner approve blocked | Creator approves own version | API blocks approval by same Owner
VER-004 | Owner khác approve | owner2 approves pending version | Version Approved and active version shows latest version
VER-005 | Previous approved archived | Approve v2 after v1 | v1 archived and v2 active
VER-006 | Reject pending version | Reject pending version | Version Rejected and active version remains latest approved
VER-007 | Reject old version regression | v4 active, reject v1/v2 old version | New request still uses v4/latest approved
VER-008 | Approve old version blocked | v4 active, try approve old pending v2/v3 | API blocks downgrade
VER-009 | SnapshotOnCreate | Create request in v1, approve v2 while running | Request keeps created version
VER-010 | LatestApproved | Workflow uses LatestApproved then approve v2 while running | Next transition uses latest approved version

## Request
Start Request / Draft
ID | Scenario | Steps | Expected
REQ-001 | Start request | Requester selects workflow, inputs first step, creates draft | Draft created successfully
REQ-002 | Required validation | Leave required field empty | Create/submit blocked with required message
REQ-003 | Optional empty field | Leave optional field empty | Request detail still shows empty field
REQ-004 | Edit draft | Open draft and edit values | Save succeeds and detail updates
REQ-005 | Submit draft | Submit draft request | Status becomes InProgress and approval step is created
REQ-006 | Cancel draft | Cancel draft | Status becomes Cancelled
REQ-007 | Cancel in progress | Cancel InProgress request if allowed | Status Cancelled and pending approvals are no longer actionable
REQ-008 | User no permission | noAccessUser opens Start Request | Private workflow is not visible

## Fields
D. Field Types
ID | Scenario | Steps | Expected
FLD-001 | Text/textarea | Input multiline text | Detail preserves line breaks
FLD-002 | Number | Input valid and invalid number | Valid saves; invalid is blocked
FLD-003 | Date/datetime | Input date and datetime | Detail formats correctly and no Invalid DataType
FLD-004 | Boolean | Check/uncheck boolean | Detail shows correct value
FLD-005 | Select static | Select one option | Value saves and reports correctly
FLD-006 | Multi-select static | Select multiple options | Detail/export show all values without layout break
FLD-007 | Select SQL query | Configure SqlQuery with dependency | Options lazy-load and reload when dependency changes
FLD-008 | Select stored procedure | Configure StoredProcedure source | Options load correctly
FLD-009 | Unsafe SQL query | Use INSERT/UPDATE/EXEC/DROP query | API blocks query
FLD-010 | File upload | Upload pdf, office file, image | Upload succeeds and detail can open file
FLD-011 | Invalid file | Upload unsupported extension | UI/API blocks file
FLD-012 | Multiple files layout | Upload many files | Detail layout does not break
FLD-013 | Stored procedure approve | Approve step with stored-procedure field | Procedure runs automatically on approve
FLD-014 | Stored procedure reject | Reject step with stored-procedure field | Procedure does not run
FLD-015 | Table manual rows | Add/remove rows and input user data | Rows save and export with Field.Column headers
FLD-016 | Table select/multi-select | Use select/multi-select columns if supported | Dropdown values save per row

## Approval
Approval Runtime
ID | Scenario | Steps | Expected
APR-001 | Approver by User | Set approver email approver1 | approver1 sees pending approval
APR-002 | Approver by Users | Set approver1 and approver2 | Only one step line is created and mode controls approval
APR-003 | Approver by Group | Set ApproverType Group | Group members see pending approval
APR-004 | WorkflowPermission approver | Use Approver/User/Owner permission | Users with permission can approve
APR-005 | NoApproval | Configure NoApproval step | Step skips or completes by configured logic
APR-006 | HOD approval | Requester has costCenter | Only mapped HOD is assigned
APR-007 | Sequential | Multiple approvers with Sequential | Approvers act in order
APR-008 | ParallelAll | Multiple approvers with ParallelAll | All approvers must approve
APR-009 | ParallelAny | MinApproveCount configured | Step passes when minimum approvals reached
APR-010 | Reject request | Approver rejects with comment | Request Rejected and requester notified
APR-011 | Next step mail | Approve step 1 to step 2 | Step 2 approvers receive mail/notification
APR-012 | Complete mail/audit | Final approver approves | Request Completed, requester notified, no duplicate Complete audit

## Routing
F. Transition Rules / Routing
ID | Scenario | Steps | Expected
RTE-001 | Default next step | No transition rule configured | Workflow follows StepOrder
RTE-002 | Field route A | ProductGroup = A | Request goes to step A
RTE-003 | Field route B | ProductGroup = B | Request goes to step B
RTE-004 | Rule priority | Multiple matching rules | Highest priority/expected rule is selected
RTE-005 | Reject to specific step | Reject rule target SpecificStep | Request returns to configured step
RTE-006 | Reject whole request | Reject rule target RejectRequest | Request becomes Rejected
RTE-007 | Alternate path | Target AlternatePath | Request moves to alternate step

## Notification
G. Notification / Email / Reminder
ID | Scenario | Steps | Expected
NOT-001 | Submit confirmation | Requester submits request | Requester receives confirmation email
NOT-002 | Approval notification | Request reaches approval step | Approver receives mail/notification with correct link
NOT-003 | Notification link | Click notification | Correct request detail/tab opens
NOT-004 | Email link tab switch | Open request from email link | Request opens and user can switch tabs
NOT-005 | Reject mail | Approver rejects request | Requester receives reject mail/notification
NOT-006 | Reminder disabled | ReminderHours null or 0 | No reminder is sent
NOT-007 | Reminder repeat | ReminderHours = 1 and no action | Reminder sends every configured interval
NOT-008 | Reminder stop | Approve/reject pending step | Reminder stops

## Report
H. Report / Export
ID | Scenario | Steps | Expected
RPT-001 | Reporter access | reporter1 opens Reports | Can see report for granted workflow
RPT-002 | Filter status/date | Filter workflow/status/from/to | Summary and rows match filters
RPT-003 | View detail from report | Click request detail in report row | Detail shows fields, values, files, table rows
RPT-004 | CSV Vietnamese font | Export CSV with Vietnamese data | Excel opens without font issue
RPT-005 | CSV headers | Export CSV | Headers use field label; table uses Field.Column
RPT-006 | CSV values | Export CSV | All field values are included
RPT-007 | JSON export | Export JSON | Includes fields, file metadata, table rows/cells

## Security
I. Security / Negative
ID | Scenario | Steps | Expected
SEC-001 | No access view | noAccessUser calls private workflow detail | 403 or hidden from UI
SEC-002 | Assigned approver without permission | Approver has no workflow permission but is assigned | Can view detail and approve assigned request
SEC-003 | Non-approver action | Other user calls approve/reject | 403 or BadRequest
SEC-004 | Viewer cannot edit | Viewer attempts workflow/request edit | Action is blocked
SEC-005 | Reporter cannot approve | Reporter attempts approve | Action is blocked
SEC-006 | SQL injection option source | Configure destructive SQL keywords | API blocks configuration/execution